Information Timeline for Teams

Advertise the Program

- Give out leaflets 6 weeks in advance.

- Take names for 2 weeks.

- Send out reminder before deadline!

- Close Program to new applicants

Establish Groups

- Allocate people to the groups.

- Set Up WhatsApp group for reminders.

- Make sure each group is given the address/location of their campfire 2 weeks before the first campfire.

Rota’s

- Distributed 2 weeks in advance of the program.

- Addresses attached for each venue.

Fire

- Campfire Packs prepared 3 weeks in advance.

- Campfire Packs distributed 1 week in advance.

Stories

- The first story - printed and distributed 4 weeks in advance of the first campfire.

- The second story - printed and distributed at the first campfire.

- The third story - printed and distributed at the second campfire.

- The fourth story - printed and distributed at the third campfire.

Songs

- Lyrics and Chords to be printed and distributed as above.